Government of the United States                         Affirmative Action Initiative for Women

NARRATIVE PROGRAM REPORT

NAME OF ORGANIZATION: AFFIRMATIVE ACTION INITIATIVE FOR WOMEN

MONTH: JANUARY, 2022

ACTIVITY NARRATIVE:

Activities / Status of project implementation Introduction The Department of State, U.S Embassy Abuja Nigeria on November 15, 2021 credited the first tranche, the account of the Affirmative Action Initiative for Women with the sum of three million, two hundred and forty thousand (N3,240,000.00)naira only to achieve the following stated Objectives: To renovate 7 classroom block at Community Primary School Isigwe Ugbawka (1,270,890.00) construct 3VIP toilets (1,040,445.00), pay salaries for the program manager (342,630.00), contractual fees for the contractors (501,795.00) and for part payment of Local transport (84,240.00). Three million (3,000,000) has been expended leaving the balance of two hundred and forty thousand (240,000) naira only. See Annex 1 for the breakdown. Clearing of site ENSUPEB addressing the pupils on the re-location to new place All the relevant stakeholders were contacted and notified accordingly and a meeting was held with the identified stakeholders to the project (NCAA, ENSUPEB, President general of the community PG, School Based Management Committee SBMC, Site Engineer, the Head Teacher and some members of the community). During the meeting, the following decisions were reached. 5 member committee comprising of the PG, SBMC, Head teacher, woman leader and Site Engineer was inaugurated to be in charge of the work. Re-location of the pupils to the nearby Community hall Upper Primary in the community Hall Mobilization and submission of quotations Mode of payment and kick off date agreed The table below shows the activities and the Status of implementation. ACTIVITIES STATUS OF PROJECT REMARKS IMPLEMENTATION Start On-going Completed Clearing of sites 18/11/2021 - 20/11/2021 Hire of contractors 18/11/2021 - 25/11/2021 Submission of Quotations 26/11/2021 - 27/11/2021 Defence of Quotations 30/11/2021 - 2/112/2021 Purchase of Materials 2/12/2021 - 2/12/2021 60%mobili. Of Contract. 2/12/2021 - 4/12/2021 Laying of Blocks 5/12/2021 18/12/2021 4/1/2022 Construction of Toilets 18/11/2021 On-going - Construction of toilets still on-going Construction of windows/doors 30/11/2021 - 29/12/2021 Finished windows ready for fixing Removal of Old Zinc 15/1/2022 - 26/1/2022

Successes of project implementation At least 60% of the work has been completed as a result of the under listed strategies in place: Effective planning and review meetings and control organized by relevant stakeholders for the project helped the project to continue despite the fact that the community did not provide their counter-part contributions, but they showed ownership of the project by ensuring safety to the materials bought. NCAA with Official from ENSUPEB having inception meeting with community leaders at the school premises Clearly written and signed Agreement on the mode of payment between NCAA and the contractors. Each contractor was to receive his/her payments in three installments (60%, 20% and 20%). Inauguration/formation of 5 member committee for the project which the head-teacher was the chairperson. Competent site engineer with requisite skills and knowledge in construction and renovation and monitoring. Availability of fund from U.S.Embassy Previously, short and incomplete Now, blocks layed to raise the demarcation and Demarcation of each class. separate each classroom. All demarcations laid and plastered. Roofing sheets and roofing materials purchased and Carpentry works on-going and available for fixing

Problems of project implementation Gross under –estimation of the project – the total number of windows in the school was 36 instead of 14 as budgeted. One classroom is as big three rooms merged together. The damage in the school is much more compared to what it was when proposed. Inflation/high cost of labour and materials. Between the proposed time and the fund release period, there was a wide and noticeable variance in the cost and price of labour and materials. For instance, a bag of cement which sold at N2, 500 at the proposing stage has increased to N4, 900, labour charged at N108, 000 by a mason has increased to N380, 000 which is more than 100% increase. Scarcity of Water in the community – A tank of 1000 liters which was sold at N5, 000 was purchased at N14, 000 because of dry season and non-availability of water in the community. Two tanks were purchased which was unbudgeted for. Attitude of some community members towards the project which would have been a disaster if not properly checkmate by the Committee. Everybody wants to be in the project. Bad terrain Sit at home and other enforced holidays disrupts the smooth running of the project. Work would have completed by March but due to the above.

Remaining Activities and Timeline S/N Activities Timeline Zincing and roofing January – February 2022 Fixing of doors &windows &outside Plastering and January-February 2022 Painting February, 2022 Digging of well Water March, 2022 (Availability of Funds 5 Putting ceiling Fans March 2022 (Availability of Funds)

Impact Statement More pupils have been enrolled into the school. The population of the school has increased from 245 to 285 in January 2022 (Head Teacher’s Statement on the 16th of January) during the review meeting with the committee. There is possibility that the school children will begin to enjoy the school feeding program of the government (ESUPEB Officials).

Annex 1- breakdown of the expenditure.

| ITEM | QTY | UNIT PRICE(#) | TOTAL PRICE(#) |
| --- | --- | --- | --- |
| Sand | 1 trip | 25,000 | 25,000 |
| Gravel | 1 trip | 48,000 | 48,000 |
| Cement | 30 bags | 4500 | 135,000 |
| Water | 2 tanks |  | 23,000 |
| Blocks | 750 | 230 | 172,500 |
| 2*3 wood | 150 | 350 | 52,000 |
| 2*4 wood | 40 | 550 | 22,000 |
| 6 Pan weight 3'' nail |  |  | 1800 |
| Planks | 20 pcs | 1200 | 24,000 |
| Binding wire | 1 roll |  | 14,000 |
| 7*7 wood | 25 | 4000 | 100,000 |
| 12MM rod | 20 | 4550 | 91,000 |
| 6MM rod |  |  | 9,500 |
| Fesher Board | 30 | 1300 | 39,000 |
| 2*4*18 wood | 20 | 900 | 18,000 |
| 3'' nail | 1 bag |  | 13,000 |
| 4'' nail | 1 bag |  | 13,000 |
| Roofing sheets | 14 bundles |  | 420,000 |
| Window | 13 | 30,000 | 390,000 |
| Doors | 6 | 31,000 | 186,000 |
| Transport for conveying materials to site |  |  | 43,200 |
| Labour for clearing of site. |  |  | 10,000 |
| Payment for Mason work |  |  | 280,000 |
| Payment for Carpentry work |  |  | 100,000 |
| Payment to Site Engineer |  |  | 200,000 |
| Payment to building Contractor |  |  | 100,000 |
| Program Officer salary for 6 months |  |  | 470,000 |
| TOTAL |  |  | 3,000,000 |